## Cover Page
<Product Name>
Prepared By:
Team X
<Team Member>: <Student Id>
<Team Member>: <Student Id>
<Team Member>: <Student Id>

## Product Backlog
Product Backlog
Story ID | Story Title | Card | Story Points | Sprint | Status | Conversation | Confirmation
BK-1 | Scalability | As a customer I would lilke to login in rental Bixi application. | 3 | Sprint 1 | In Progress | This is the basic login screen that user enter username and password | 1. User can login after putting proper credentials 2.Screen disply message to custmer if username or passwors is not correct
BK-2 | Functionality | As a customer I would like see all Bixi Bike location in application | 4 | Sprint 1 | In Progress | This will allow the customer to select see all locations about Bxi Bike | 1. Customer can see all locations about Bixi Bike 1. Customer could select which locations is close to rent Bixi Bike
|  | As a customer I would like to know how many bike are availble in each location | 4 | Sprint 1 | In Progress | This will allow customer knows how many bikes are available at location | 1- Customer can see how many bikes are availeble in real time
| Functionality | As a customer I would like the real-time bike availability | 4 | Sprint 1 | In Progress | This will allow the customer see which bikes available in real time | 1- Customer can see quickly and easily find a bike to rent
| Functionality | As a customer I would like reserve selected Bixi bike |  | Sprint 1 | In Progress | This will allow customer reserve selected Bixi bike and help customer to reserve Bixi bike andthen rent it | 1. Customer can reserve Bixi bike in special location
|  | As a customer I would l like to new payment option | 4 | Sprint 1 | In Progress | This will help customer to easily and quickly do all steps that needs to rent Bixi bike | 1- Customer can quickly finish all process for rent Bixi bike with this option
|  | As a customer I would like to cancle my reservation | 4 | Sprint 1 | In Progress | This will help customer to cancle reservation without phone call | 1- Customer can cancle Bixi Bike reservation without need to phone call and speak with customer service
|  | As a customer I would like to know Improved bike maintenance: | 4 | Sprint 1 | Not in sprint | This will help customer know better tracking and maintenance of bikes to ensure they are in good condition and available for rent at all time | 1- Customer can track and know status about bikes in any locations 2- this option can help customer to know real status about any bikes in location to manage time and make deision about rent it

## Sprint 1
Sprint 1 Backlog
Sprint 1 Goal(s): <Describe what you would like to achieve at the end of sprint 1>
Story ID | Task ID | Task Title | Task Description | Ideal Hours | Status | Comments
BK-1 | BK-1.1 | Create Register and login form and develop | Creat register and login UI form so customer can have register and then login in Rental Bixi Bike application, Develop user registration functionality that allows users to create an account with their personal information and payment details | 10 hrs | Planned | We create register and login UI form, this form has validation if user enter wrong user name and password shows error message
BK-2 | BK-2.1 | Bike Listing Page | Create a page that displays the available bikes for rent, including their pictures, descriptions, and rental rates | 8 hrs | In Progress | We create facility with create button on form when customer click on it can show customer all Bixi bike location
BK-3 | BK-3.1 | Booking Form | Build a form that allows users to select the bike they want to rent and specify the rental dates, and displays the total cost of the rental | 8hrs | In Progress | we decide have this form that customer can select bike in specific location in specific dates, also we need to show cost for rent bixi bike
BK-4 | BK-4.1 | Rental History | Create a page where users can view their rental history, including the bikes they rented and the rental dates and costs | 8hrs | Planned | we decide have this option that customer can do payment safe and easily with this app.we should more search about app security